Risk Register

Probability is assigned according to this scale : minimal, moderate, high.
Damage is assigned according to this scale: minimal,tolerable,serious, devastating.

Risk Type	Risk	Probability	Damage	Control(s)
Requirements	Supplied misinformation (accidentally or otherwise) by other students we interview.	High	Serious	2
Requirements	Fail to implement and evaluate a poorly understood feature in prototyping stage, leading to an incomplete understanding at the time of implementation.	Moderate	Moderate/Serious	7
Organisational	Unclear, overlapping roles leading to confusion over who is assigned to what.	High	Serious	3
Tools	PMS account revoke or failure	Minimal	Devastating	4
Tools	Git failure	Minimal	Serious	4
Estimation	Task estimations inaccurate	High	Serious	5
People	Team member absent for extended period	Minimal	Devastating	6

Controls

Control	Description
1	Thorough preparation for requirements gathering should be carried out, including questions and a pre agreed strategy where possible. There should always be two notetakers where possible and the use of audio recording is encouraged if suitable.
2	Interview as many separate groups as possible. Do not include any requirements gathered in these interviews unless it is verified by multiple teams. If in doubt stick with the requirements we gather ourselves.
3	Continually review organisation plan document and post current tasks with members working on them to project management system.
4	All files should be backed up in multiple places wherever possible so at least a relatively recent copy is available (this is largely facilitated by git automatically). A good approach is that all documents typed or uploaded directly to the PMS should have a copy entered into Git and vice versa. If a system fails, the Toolsmith and Configuration Manager will be responsible for repairing the system or activating a contingency system. With this in place files can be restored as quickly as possible.
5	Deliberately set task deadlines a day or two ahead of them actually being needed (depending on the task size and time available) to leave room for estimation errors. Obviously we have no control over deliverable submission dates, but we should aim to have the work required completed in advance to allow for estimation error. If a task is going to run late this should be raised with the team immediately so we can attempt to push its completion however possible.
6	Each team member must document what they are working on so it can be continued by another team member in their absence. The role duties of the missing member should be distributed evenly as soon as possible. Particularly if the Project Manager becomes absent the task of scheduling meeting agendas should be assigned to one other member to keep the project coherent.
7	High priority/poorly understood features should be implemented first followed by successfully low priority features. If necessary use techniques such as Wizard of Oz prototyping to produce something which can be evaluated.

Appendix

Previous Risks

Risk Type	Risk	Probability	Damage	Control(s)
Requirements	Capture incorrect requirements from client interview.	Moderate	Serious	1
Requirements	Capture incorrect requirements from stakeholder panel.	Moderate	Serious	1
Requirements	Wrong/Misunderstood requirements at bash prototype stage.	Moderate	Devastating	1,2

Change Log

Version	Updates/Changes	Date
1.0	Produced initial risk register containing foreseen risks and controls	10/10/2012
2.0	New risks assessed and section introduced to contain risks which are no longer 'active' in appendix. / Unclear overlapping roles promoted to high probability whilst chance of capturing incorrect requirements at various stages demoted to moderate probability	21/20/2012
2.1	New risk and control added. Risk probabilities reassessed.	6/11/2012